## ProjectSchedule
Create a Project Schedule in this worksheet. Enter title of this project in cell B1. Information about how to use this worksheet, including instructions for screen readers and the author of this workbook is in the About worksheet. Continue navigating down column A to hear further instructions. | eRPMES Cagayan Valley
Enter Company Name in cell B2. | Agile Methodology Approach
Enter the name of the Project Lead in cell B3. Enter the Project Start date in cell E3. Pooject Start: label is in cell C3. | ICTS and NRO II | Project Start: |  | 2022-04-13
The Display Week in cell E4 represents the starting week to display in the project schedule in cell I4. The project start date is considered Week 1. To change the display week, simply enter a new week number in cell E4. The starting date for each week, starting with the display week from cell E4, starts in cell I4 and is auto calculated. There are 8 weeks represented in this view from cell I4 through cell BF4. You should not modify these cells. Display Week: label is in cell C4. |  | Display Week: |  | 1 |  |  | 2022-04-11 | [6 empty] | 2022-04-18 | [6 empty] | 2022-04-25 | [6 empty] | 2022-05-02 | [6 empty] | 2022-05-09 | [6 empty] | 2022-05-16 | [6 empty] | 2022-05-23 | [6 empty] | 2022-05-30 | [6 empty] | 2022-06-06 | [6 empty] | 2022-06-13 | [6 empty] | 2022-06-20 | [6 empty] | 2022-06-27 | [6 empty] | 2022-07-04 | [6 empty] | 2022-07-11 | [6 empty] | 2022-07-18 | [6 empty] | 2022-07-25 | [6 empty] | 2022-08-01 | [6 empty] | 2022-08-08 | [6 empty] | 2022-08-15 | [6 empty] | 2022-08-22 | [6 empty] | 2022-08-29 | [6 empty] | 2022-09-05 | [6 empty] | 2022-09-12 | [6 empty] | 2022-09-19 | [6 empty] | 2022-09-26 | [6 empty] | 2022-10-03 | [6 empty] | 2022-10-10 | [6 empty] | 2022-10-17 | [6 empty] | 2022-10-24 | [6 empty] | 2022-10-31
Cells I5 through BL5 contain the day number for the week represented in the cell block above each date cell and are auto calculated. You should not modify these cells. Today's date is outlined in Red (hex #AD3815) from today's date in row 5 through the entire date column to the end of the project schedule. | time axis 2022-04-11 to 2022-11-06
This row contains headers for the project schedule that follows below them. Navigate from B6 through BL 6 to hear the content. The first letter of each day of the week for the date above that heading, starts in cell I6 and continues through cell BL6. All project timeline charting is auto generated based on the start and end dates entered, using conditional formats. Do not modify content in cells within columns after column I starting with cell I7. | TASK | ASSIGNED TO | PROGRESS | START | END | DAYS | time axis 2022-04-11 to 2022-11-06
Do not delete this row. This row is hidden to preserve a formula that is used to highlight the curren day within the project schedule.
Cell B8 contains the Phase 1 sample title. Enter a new Title in cell B8. Enter a name to assign the phase to, if it applies for your project, in cell C8. Enter Progress for the entire phase, if it applies for your project, in cell D8. Enter the start and end dates for the entire phase, if it applies for your project, in cells E8 and F8. The Gantt chart will automatically fill in the appropriate dates and shade according to the progress entered. To delete the phase and work only from tasks, simply delete this row. | Phase 1 Project Preparation and Requirements Gathering |  | 86% | 2022-04-13 | 2022-04-18 | 6
Cell B9 contains the sample task "Task 1." Enter a new task name in cell B9. Enter a person to assign the task to in cell C9. Enter progres of the task in cell D9. A progress bar appears in the cell and is shaded according to the number in the cell. For example, 50 percent progress would shade half of the cell. Enter task start date in cell E9. Enter task end date in cell F9. A status bar shaded for the dates entered appears in blocks starting from cell I9 through BL9. | Project Discussion | HRV, SMD, RGJ & RPB | 100% | 2022-04-13 | 2022-04-13 | 1
| Draft Gantt Chart | HRV & SMD | 100% | 2022-04-13 | 2022-04-13 | 1
Rows 10 through 13 repeat the pattern from row 9. Repeat the instructions from cell A9 for all task rows in this worksheet. Overwrite any sample data. A sample of another phase starts in cell A14. Continue entering tasks in cells A10 through A13 or go to cell A14 to learn more. | Draft flow Chart | HRV & SMD | 90% | 2022-04-16 | 2022-04-18 | 3
| Provide Sample Reports/Forms | IND | 40% | 2022-05-20 | 2022-06-17
| Setting up of Laravel Project and GitHub | RGJ | 100% | 2022-04-16 | 2022-04-18 | 3
The cell at right contains the Phase 2 sample title. You can create a new phase at any time within column B. This project schedule does not require phases. To remove the phase, simply delete the row. To create a new phase block in this row, enter a new Title in cell at right. To continue adding tasks to the phase above, enter a new row above this one and fill in the task data as in cell A9's instruction. Update the Phase details in cell at right based on cell A8's instruction. Continue navigating down column A cells to learn more. If you haven't added any new rows in this worksheet, you will find 2 additional sample phase blocks have been created for you in cells B20 and B26. Otherwise, navigate through column A cells to find the additional blocks. Repeat the instructions from cells A8 and A9 whenever you need to. | Phase 2 Helpdesk Form Development |  | 85.56% | 2022-04-16 | 2022-06-30 | 76
| Development of Login Module | RGJ | 100% | 2022-04-16 | 2022-04-17 | 2
| Development of Forgot Password Module | RGJ | 100% | 2022-04-18 | 2022-04-19 | 2
| Development of User Registration | RGJ | 100% | 2022-04-20 | 2022-04-22 | 3
| Development of Profile Update Module | HRV & SMD | 100% | 2022-04-25 | 2022-08-27 | 125
| Development of User Management Module | HRV & SMD | 100% | 2022-04-28 | 2022-05-02 | 5
| Development of Issue Management Module | HRV & SMD | 100% | 2022-05-03 | 2022-05-06 | 4
| Development of Holiday Management Module | HRV & SMD | 0% | 2022-06-13 | 2022-06-17
| Development of Role Management Module | HRV, SMD & RGJ | 100% | 2022-05-07 | 2022-05-11
| Development of Request Module (Admin/HOD View) | HRV, SMD & RGJ | 100% | 2022-05-12 | 2022-06-30 | 50
| Development of Request Module (Tech View) | HRV, SMD & RGJ | 100% | 2022-05-13 | 2022-06-30 | 2022-05-13
| Development of Request Module (User View) | HRV, SMD & RGJ | 100% | 2022-05-14 | 2022-06-30
| Development of Dashboard (Admin/HOD View) | HRV, SMD & RGJ | 100% | 2022-05-15 | 2022-06-30
| Development of Dashboard (Tech View) | HRV, SMD & RGJ | 100% | 2022-05-16 | 2022-06-30
| Development of Dashboard (User View) | HRV, SMD & RGJ | 100% | 2022-05-17 | 2022-06-30
| Development of Auto Assign Function | RGJ | 100% | 2022-05-18 | 2022-06-30
| Development of Report Module | HRV, SMD & RGJ | 0% | 2022-06-20 | 2022-06-24
| Checkpoint Meeting | IND, ISDD & OJTs | 100% | 2022-05-20 | 2022-05-20
| Reflect Comments/Recommendations | HRV, SMD & RGJ | 40% | 2022-05-20 | 2022-06-30
Sample phase title block | Phase 3 System Testing and Trainings |  | 0% | 2022-07-01 | 2022-08-05 | 36
| Presentation to ICTS | ICTS and OJTs | 0% | 2022-07-01 | 2022-07-01 | 1
| Consolidate Comments/Recommendations | HRV, SMD & RGJ | 0% | 2022-07-01 | 2022-07-01 | 1
| Reflect Comments/Recommendations | HRV, SMD & RGJ | 0% | 2022-07-01 | 2022-07-08 | 8
| Go Live Activities | HRV, SMD & RGJ | 0% | 2022-07-11 | 2022-07-13 | 3
| Testing Phase | ICTS and Other NEDA Staff(End User) | 0% | 2022-07-14 | 2022-07-20 | 7
| Users Trainings (All NEDA Staff) | All NEDA Staff | 0% | 2022-07-21 | 2022-07-22
| Reflect Comments/Recommendations | RGJ | 0% | 2022-07-25 | 2022-08-12 | 19
Sample phase title block | Phase 4 Launching, System Maintenance |  |  | 2022-08-15 | 2022-08-18 | 4
| System Launching | ICTS | 0% | 2022-08-15 | 2022-08-16 | 2
| System Updates | ICTS | 0% | 2022-08-17 | 2022-08-18
This is an empty row
This row marks the end of the Project Schedule. DO NOT enter anything in this row. Insert new rows ABOVE this one to continue building out your Project Schedule. | Insert new rows ABOVE this one

## List Of Enhancements
List of enhancements based on May 20 2022 meeting
# |  | Role | Module | Assigned To | Status
1 | Change label from 'Pending' to 'Ongoing' | User | Dashboard - Index | Shaina | Done
2 | Replace delayed card to completed card | User | Dashboard - Index | Shaina | Done
3 | Add confirmation dialog to 'Rate' button | User | Request - Edit | Henry | Done
4 | Required reason for low rating(1 & 2) | User | Request - Edit | Henry | Done
5 | Show rating in words | User | Request - Edit | Henry | Done
6 | Move cards(Total, Ongoing and Complete) from dashboard to request module | User | Request - Index | Shaina | Done
7 | Remove prioritization option | User | Request - Edit & Create | Shaina\Henry | Done
8 | Change edit icon to 'eye' | User | Request - Index | Henry | Done
9 | Remove assigned and rejected status | Technician | Request - Edit | Shaina | Done
10 | Change label from 'Rejected' to 'Invalid' | User/Admin/HOD/Technician | Database Table - statuses | Shaina | Done
11 | Add confirmation dialog to 'Delete' button | Admin/HOD/User | Request - Index | Shaina | Done
12 | Add 'as of today' label for all cards | Admin/HOD/Technician | Dashboard - Index | Shaina | Done
13 | Add date duration for all issue types | Admin | Issue Type - Index, Edit & Create | Shaina\Henry | Waiting for docs
14 | Add 'Holiday' and 'Role' module (aka Maintenance Table) | Admin | Holiday and Role | Lands | Ongoing
15 | Delete function for User(Submitted Only) and Admin only | Admin/User | Request - Index | Lands
16 | Exclude weekends and holidays for the computation of delayed ticket | Admin/HOD | Request and CRON job | Lands
17 | Use date duration from issue type for the computation of delayed ticket | Admin/HOD | Request and CRON job | Lands
18 | Add auto rating job for tickets older than 3 days |  | CRON job | Lands
19 | Show notify card if user have pending(for rating) tickets | User | Request - Index | Lands
20 | Add NEDA header | User/Admin/HOD/Technician | Dashboard - Index | Shaina\Henry
21 | Add VOIP number per office/user | Admin | User and Staff Module | Shaina\Henry | Ongoing
22 | Remove personal information and use VOIP instead | User/Admin/HOD/Technician | Request - Edit | Shaina\Henry | Ongoing
23 | Only HOD and Admin can reject ticket | Admin/HOD | Request - Edit | Lands
24 | Include monthly and quarterly reports | Admin/HOD | Report | Lands | Waiting for docs
25 | Use MS365 account as login | User/Admin/HOD/Technician | Login | Lands | Done
Difficulty :
Simple
Intermediate
Complex

## Pending Docs
Info | Stat
1. List of Staff/Office from MS365 with VOIP number | Ok
2. List of Position from MS365 | Ok
3. List of Issues with number of days to resolve and troubleshooting steps if available
4. Rating descriptions
5. Sample reports submitted by tech/hod (monthly/quarterly)
6. Email info for email notification
- 6.a email address
- 6.b password
- 6.c host (eg. smtp.gmail.com)
- 6.d encryption (eg. tls)
- 6.e port